# Internet Safety Curriculum Proposal_-  DRAFT_________________

Goal

To develop and implement curriculum that teaches elementary students safe, effective, and ethical use of the Internet.

Objectives

- Build cadre of up to 16 K-6 computer lab resource teachers and/or classroom teachers

- Cadre becomes i-Safe certified

- Cadre develops, tests, and refines lessons and resources that will be accessible to all computer resource teachers at elementary sites.

- Publish and deliver at least one online lesson tied to an Open Court theme per grade level (K-6).

Funding

Technology Services plans to submit a workshop proposal to Curriculum and Professional Learning  in order to compensate cadre teachers with professional hours on the salary schedule. If funding becomes available, teachers may opt for a stipend.

Commitment

15 hours of professional development

Expansion Plan

Based on outcome of elementary implementation, committee will reconvene to propose secondary component of Internet Safety Curriculum Plan. Expansion plan will build on scope and sequence of elementary plan.

_______________________________________________________________

Tentative Timeline 2008-2009

March

- Present project to ETAC

- Get feedback on teaming procedure

- Create survey to assess interest

April

- Select and notify teachers

- Offer 2-day i-Safe certification class at Tech Services = 5 hrs (Tues/Wed)

- Cadre meets to review resources and lesson template, brainstorming lesson ideas using “lesson sharing” model = 2 hrs

May

- Teacher teams begin lesson development = 2 hrs

- Teachers test lessons at their sites = 3 hrs

- Cadre meets to share and refine lessons = 2 hrs

June – August

- Meet with steering committee (to be determined) to present project and lessons

- Adjust project goals and lessons, if needed, based on committee feedback

September

- Cadre teachers will showcase project, resources, and lessons to all elementary resource teachers